MR. BOBA TEA

COMPLETE LAUNCH CHECKLIST

From Search to Opening Week  |  Khammam, Telangana

| Total Phases: 7 Total Tasks: 74 | Timeline: ~8-12 Weeks Budget: ₹3-5L (Lean) / ₹8-10L (Premium) |
| --- | --- |

| 🔍 PHASE 1: LOCATION SCOUTING & SHOP SEARCH | Week 1-2 |
| --- | --- |

| ✔ | TASK | PRIORITY | EST. COST | DONE |
| --- | --- | --- | --- | --- |
| ☐ | Walk Wyra Road end-to-end (KFC to Lakaram Lake stretch) Note every vacant shutter, phone numbers on To-Let boards, foot traffic patterns | CRITICAL | Free |  |
| ☐ | Scout Yellandu X Roads / IT Hub area specifically Best micro-location. Check ground-floor shops within 100m of IT Hub entrance | CRITICAL | Free |  |
| ☐ | Scout VVC Complex area (near Tanishq / Fashion Factory) Premium retail strip. Check for small 100-200 sq ft spaces | HIGH | Free |  |
| ☐ | Scout near KFC / Domino's on Wyra Road Food corridor. Look for shop within 200m of KFC, same side of road | HIGH | Free |  |
| ☐ | Scout Mamata Medical College / Gollagudem Road area Waffle Co already thriving here. Thousands of medical students | MEDIUM | Free |  |
| ☐ | Scout Lakaram Park Road / Kaviraj Nagar junction Where Wyra Rd meets lake area. Evening + weekend crowd | MEDIUM | Free |  |
| ☐ | Contact 3-5 local property brokers via JustDial Search 'property dealers Khammam'. They know every vacant shutter | CRITICAL | Free |  |
| ☐ | Check OLX Khammam for commercial shop listings olx.in/khammam > Shops & Offices for Rent. New listings weekly | HIGH | Free |  |
| ☐ | Join Khammam Facebook groups for property leads Search 'Khammam properties', 'Khammam real estate' groups | HIGH | Free |  |
| ☐ | Evaluate shortlisted shops using scouting checklist Road-facing? Foot traffic after 4 PM? College/IT within 200m? Parking? Electricity/water? | CRITICAL | Free |  |
| ☐ | Visit shortlisted shops at 3 different times of day Morning (10 AM), afternoon (2 PM), evening (6 PM) to verify traffic patterns | HIGH | Free |  |
| ☐ | Negotiate rent and finalize shop Target: ₹8-15K/month for 100-200 sq ft on Wyra Road. Get 3-month deposit if possible | CRITICAL | ₹24-45K deposit |  |

| 📋 PHASE 2: LEGAL & LICENSING | Week 2-3 |
| --- | --- |

| ✔ | TASK | PRIORITY | EST. COST | DONE |
| --- | --- | --- | --- | --- |
| ☐ | Apply for FSSAI Food License (Basic or State) Basic for <₹12L turnover. Apply online at foscos.fssai.gov.in. Takes 7-30 days | CRITICAL | ₹2-5K |  |
| ☐ | Get Khammam Municipal Trade License Visit Khammam Municipal Corporation office. Required for any commercial shop | CRITICAL | ₹1-3K |  |
| ☐ | Register for GST (if turnover will exceed ₹20L) Can skip initially if under threshold. Register at gst.gov.in | MEDIUM | Free |  |
| ☐ | Get Shop & Establishment Act registration Labour Department, Telangana. Required within 30 days of opening | HIGH | ₹500-1K |  |
| ☐ | Open a current account for Mr. Boba Tea Any bank. Needed for UPI business payments, Swiggy/Zomato payouts | HIGH | Free |  |
| ☐ | Get fire safety certificate (if required by municipal corp) Check with local municipal office. May not be required for small shops | MEDIUM | ₹1-2K |  |
| ☐ | Sign formal rental agreement (stamp paper) 11-month agreement on ₹100 stamp paper. Include rent, deposit, lock-in terms | CRITICAL | ₹500-1K |  |

| 🛒 PHASE 3: SUPPLIER SOURCING & PROCUREMENT | Week 2-4 |
| --- | --- |

| ✔ | TASK | PRIORITY | EST. COST | DONE |
| --- | --- | --- | --- | --- |
| ☐ | Contact The Tea Planet (Hyderabad) for raw materials Primary supplier. Tapioca pearls, syrups, powder mixes, popping boba. Get catalog + pricing | CRITICAL | Free inquiry |  |
| ☐ | Contact QQS Bubble Tea (Delhi) as backup supplier Compare pricing, shipping costs, MOQ with The Tea Planet | HIGH | Free inquiry |  |
| ☐ | Browse IndiaMART for equipment pricing Sealing machine, shaker, blender, fructose dispenser, ice maker. Compare 3+ vendors | CRITICAL | Free inquiry |  |
| ☐ | Order sealing machine (cup sealer) Manual or semi-auto. ₹15-25K. Lead time: 3-7 days | CRITICAL | ₹15-25K |  |
| ☐ | Order cocktail shaker set + measuring tools Shaker cups, jiggers, long spoons. ₹18-28K for professional set | CRITICAL | ₹18-28K |  |
| ☐ | Order commercial blender For fruit-based drinks. ₹8-15K | HIGH | ₹8-15K |  |
| ☐ | Order fructose dispenser For consistent sugar levels. ₹12-22K | HIGH | ₹12-22K |  |
| ☐ | Order commercial refrigerator For milk, fruits, toppings storage. ₹18-30K | CRITICAL | ₹18-30K |  |
| ☐ | Order ice maker machine ₹15-25K. Essential for boba drinks | CRITICAL | ₹15-25K |  |
| ☐ | Order induction cooktop For cooking tapioca pearls. ₹3-6K | HIGH | ₹3-6K |  |
| ☐ | Order first batch of cups, sealing film, straws, lids 500-1000 cups each size to start. Source from IndiaMART or local packaging market | CRITICAL | ₹8-14K |  |
| ☐ | Order first batch of raw materials Tapioca pearls, syrups (6-8 flavors), popping boba, jellies, milk, sugar | CRITICAL | ₹18-33K |  |
| ☐ | Source fresh fruits from local Khammam wholesale market Mangoes, strawberries, passion fruit. Visit main wholesale market for pricing | HIGH | ₹2-4K |  |

| 🏠 PHASE 4: SHOP SETUP & INTERIOR | Week 3-5 |
| --- | --- |

| ✔ | TASK | PRIORITY | EST. COST | DONE |
| --- | --- | --- | --- | --- |
| ☐ | Deep clean the shop space Walls, floor, ceiling. Pest control treatment before setup | CRITICAL | ₹2-3K |  |
| ☐ | Paint walls (bright, Instagrammable colors) Pink/purple/teal theme matching Mr. Boba Tea branding. White base + accent wall | HIGH | ₹5-10K |  |
| ☐ | Install service counter with workspace behind L-shape or straight counter. Space for equipment, prep area, and POS | CRITICAL | ₹10-20K |  |
| ☐ | Set up equipment station behind counter Sealer, shaker area, blender, fructose dispenser, induction cooktop in workflow order | CRITICAL | Included above |  |
| ☐ | Install menu board (LED/printed backlit) 5-column ordering flow: Size > Category > Sugar > Ice > Toppings | CRITICAL | ₹3-8K |  |
| ☐ | Get neon sign made ('Mr. Boba Tea' or boba cup shape) Custom LED neon. Major visibility + photo magnet. Front-facing for road visibility | HIGH | ₹3-8K |  |
| ☐ | Set up 2-3 small seating tables + stools (4-8 seats) Compact cafe-style. Even standing counter with stools works for small space | MEDIUM | ₹5-12K |  |
| ☐ | Install adequate lighting (warm white + accent) Bright enough for photos, warm enough for ambiance. LED strips on counter/ceiling | HIGH | ₹3-6K |  |
| ☐ | Create selfie wall / photo spot One wall with cute backdrop — boba graphics, neon sign, colorful paint. Free marketing when customers post | HIGH | ₹2-5K |  |
| ☐ | Install wash basin / sink with running water Essential for hygiene + FSSAI compliance | CRITICAL | ₹3-5K |  |
| ☐ | Set up waste bins (wet + dry separation) Behind counter for prep waste, 1 customer-facing bin | HIGH | ₹500-1K |  |
| ☐ | Install UPI QR code / POS terminal PhonePe/GPay/Paytm business QR. Most Khammam customers pay via UPI | CRITICAL | Free |  |

| 👨‍🍳 PHASE 5: MENU, TRAINING & TESTING | Week 4-6 |
| --- | --- |

| ✔ | TASK | PRIORITY | EST. COST | DONE |
| --- | --- | --- | --- | --- |
| ☐ | Finalize 12-16 launch flavors after taste testing 6-8 fruit-based + 6-8 milk-based. Test with family/friends first | CRITICAL | ₹2-3K (testing) |  |
| ☐ | Set final pricing: Small / Medium / Large Recommended launch: ₹99 / ₹149 / ₹199 (lower than plan to drive trial) | CRITICAL | N/A |  |
| ☐ | Create 'New to Boba? Try This!' recommendation list Top 3 crowd-pleasers for first-timers: Mango, Classic Milk Tea, Chocolate | HIGH | N/A |  |
| ☐ | Train yourself on making every drink consistently Practice 50+ drinks before opening. Timing, proportions, sealing, presentation | CRITICAL | Included in materials |  |
| ☐ | Hire Barista #1 (and helper if budget allows) Local hire, ₹10-12K/month. Train them for 1 week before opening | HIGH | ₹10-12K/mo |  |
| ☐ | Train staff on 5-step ordering flow Size > Category & Flavor > Sugar Level > Ice Level > Toppings. Must be smooth | CRITICAL | N/A |  |
| ☐ | Do 2-3 dry runs (friends & family soft launch) Invite 10-15 people. Full ordering experience. Get honest feedback. Fix issues | CRITICAL | ₹2-4K |  |
| ☐ | Standardize recipes with exact measurements Write down every recipe: ml of syrup, grams of pearls, ice level, shake count | CRITICAL | N/A |  |
| ☐ | Set up inventory tracking (even a simple notebook) Track daily: cups used, pearls consumed, syrup levels. Know when to reorder | HIGH | Free |  |
| ☐ | Register on Swiggy & Zomato as restaurant partner Apply at partner.swiggy.com and partner.zomato.com. Takes 5-10 days for approval | HIGH | Commission-based |  |

| 📣 PHASE 6: PRE-LAUNCH MARKETING | Week 5-7 |
| --- | --- |

| ✔ | TASK | PRIORITY | EST. COST | DONE |
| --- | --- | --- | --- | --- |
| ☐ | Design logo for Mr. Boba Tea Get it done on Fiverr/Canva or local designer. Cute boba cup character works well | CRITICAL | ₹2-5K |  |
| ☐ | Create Instagram & Facebook pages @mrbobatea_khammam. Post teaser content: 'Something new is coming to Khammam!' | CRITICAL | Free |  |
| ☐ | Set up Google Business Profile Claim 'Mr. Boba Tea Khammam'. Add photos, menu, hours. Dominate local search | CRITICAL | Free |  |
| ☐ | Identify 5-8 local Khammam food bloggers/influencers 5K-20K followers. Invite for free tasting 3-5 days before opening | HIGH | ₹2-3K (free drinks) |  |
| ☐ | Print 200 posters for colleges, coaching centers, bus stand A3 size, colorful, with opening date + 'First 50 customers FREE' offer | HIGH | ₹2-3K |  |
| ☐ | Create WhatsApp broadcast list / group Every friend, relative, contact in Khammam. Ask them to share on their status | HIGH | Free |  |
| ☐ | Run Facebook ad for grand opening (geo-targeted) 15-20 km radius around Khammam, ages 15-40, ₹3-5K budget for 1 week | HIGH | ₹3-5K |  |
| ☐ | Plan grand opening day offer First 50 customers free small boba / BOGO deal / flat ₹49 for any drink on Day 1 | CRITICAL | ₹3-5K |  |
| ☐ | Prepare free sampling cups (100-200 small samples) 4 oz cups with mango or classic milk tea. Hand out near colleges, IT Hub, bus stand | CRITICAL | ₹2-3K |  |

| 🎉 PHASE 7: OPENING WEEK (Day 1-7) | Week 7-8 |
| --- | --- |

| ✔ | TASK | PRIORITY | EST. COST | DONE |
| --- | --- | --- | --- | --- |
| ☐ | DAY 1: Grand Opening! Execute opening day offer Be there from setup to close. Document everything. Take photos/videos for social media | CRITICAL | Budgeted above |  |
| ☐ | DAY 1: Hand out free samples outside shop to passersby Have a person standing with a tray near the road. Pull people in with free taste | CRITICAL | Budgeted above |  |
| ☐ | DAY 1-3: Post stories/reels of every customer (with permission) Tag customers on Instagram. They reshare = free reach to their followers | HIGH | Free |  |
| ☐ | DAY 1-3: Ask every customer to leave Google review Target 30-40 five-star reviews in first week. Show QR code at counter for easy review | CRITICAL | Free |  |
| ☐ | DAY 1-7: Track daily customer count, revenue, popular flavors Simple notebook or phone note. Morning/afternoon/evening split. Identify patterns | CRITICAL | Free |  |
| ☐ | DAY 2-3: Run 'Post on Instagram, get 10% off' promotion Customers post photo with location tag = discount on next drink. Viral loop | HIGH | 10% discount |  |
| ☐ | DAY 3-4: Walk to nearby colleges/IT Hub with sample tray Lunch break (12-1 PM) or college exit time (4-5 PM). Hand out with business card | HIGH | ₹1-2K |  |
| ☐ | DAY 4-5: Analyze first 3 days: What's selling? What's not? Identify top 3 flavors, dead flavors, peak hours, avg ticket size. Adjust menu if needed | CRITICAL | N/A |  |
| ☐ | DAY 5-6: Reorder raw materials if running low Check pearl stock, syrup levels, cup inventory. Never run out in week 1 | HIGH | As needed |  |
| ☐ | DAY 7: Week 1 review — customers/day, revenue, feedback Calculate: avg daily customers, avg ticket size, total revenue, top flavors, issues to fix | CRITICAL | N/A |  |
| ☐ | DAY 7: Plan Week 2 strategy based on Week 1 data Double down on what's working. Fix what's broken. Set Week 2 daily target | HIGH | N/A |  |
| ☐ | DAY 7: Send thank-you WhatsApp to all Week 1 customers If you collected numbers, send personalized thank you + 'come back for 10% off' offer | MEDIUM | Free |  |

# KEY NUMBERS TO REMEMBER

| Survival Threshold | 20 customers/day minimum |
| --- | --- |
| Week 1 Target | 30-50 customers/day (novelty buzz) |
| Month 3+ Target | 30-40+ customers/day (regulars) |
| Break-even | 4-8 months |
| Gross Margin per Drink | 65-79% |
| Monthly Fixed Costs | ₹59K-1.13L |
| Kill Switch | If <15/day after 4 months, reassess |

# NOTES & REMINDERS

- Owner presence is MANDATORY in Year 1. Cannot run this remotely.

- Start leaner than planned. Validate demand before investing heavily in interior.

- Free sampling is the #1 strategy for educating a market that doesn't know boba yet.

- Train staff to recommend crowd-pleasers (mango, chocolate) to first-timers, not adventurous flavors (taro).

- Pricing can always be raised later. It's very hard to lower prices once set. Start at ₹99-149-199.

- WhatsApp word-of-mouth is more powerful than Instagram in Tier 2 cities. Every customer's status reaches 200+ contacts.

- You have a 12-24 month monopoly window before franchise chains arrive. Execute fast.

Good luck, Chris! Mr. Boba Tea is going to crush it in Khammam.